## Sheet1
Task | Task Type | WBS code
Stage 0 - Mobilization | Location | 1
Preparation work | Work | 1.1
Celtņta mobilizacija | Work | 1.1.1
Electricity | Work | 1.1.1.1
Foundation as-built | Work | 1.1.1.2
Floor 1 | Location | 2
Assembly | Work | 2.1
Survey | Work | 2.1.1
CSW (Start assembly) | Work | 2.1.2
COW | Work | 2.1.3
CSF | Work | 2.1.4
CSL | Work | 2.1.5
Ventilacijas šahtas | Work | 2.1.6
HCS | Work | 2.1.7
CMS | Work | 2.1.8
Other works | Work | 2.2
Vertikalas šuves | Work | 2.2.1
HCS veidņi | Work | 2.2.2
HCS stiegrojums | Work | 2.2.3
HCS betons | Work | 2.2.4
Floor 2 | Location | 3
Assembly | Work | 3.1
Survey | Work | 3.1.1
CSW | Work | 3.1.2
COW | Work | 3.1.3
CSF | Work | 3.1.4
CSL | Work | 3.1.5
Ventilacijas šahtas | Work | 3.1.6
HCS | Work | 3.1.7
CMS | Work | 3.1.8
Other works | Work | 3.2
Wall grounting | Work | 3.2.1
HCS Formwork | Work | 3.2.2
HCS Reinforcement | Work | 3.2.3
HCS Concreting | Work | 3.2.4